SLS-INTERNAL // INTERNAL USE ONLY

# HERON (SLS-101) — Weekly Program Status

| PROGRAM | Slackwater / HERON / SLS-101 |
| --- | --- |
| PERIOD | Week of 02 Feb 2026 |
| PM | M. Calder |
| OVERALL | GREEN |

RAG Summary

| Area | Status | Comment |
| --- | --- | --- |
| Schedule | GREEN | Sea-trial window holding for late Mar. |
| Cost | AMBER | Battery module invoice (INV-20547) over plan. |
| Technical | GREEN | Endurance test hit 58 days on bench. |
| Supply | AMBER | Hydrophone lead time slipped 2 weeks. |

Upcoming Milestones

| Milestone | Target | Status |
| --- | --- | --- |
| Endurance bench test complete | 2026-02-14 | On track |
| Integrated sea trial #1 | 2026-03-27 | On track |
| Customer demo | 2026-05-09 | Planning |

Top Risks

Hydrophone supply slip could push trial #2; mitigation: alternate vendor qualification underway.

Battery cost variance under review with Finance; not yet a breach.