## Slide 1
HERON (SLS-101) Program Review
Slackwater — Long-Endurance ISR Surface Vehicle
Monthly program review · 15 January 2026
SLS-INTERNAL // INTERNAL USE ONLY · Salish Littoral Systems · 535 4th St, Bremerton, WA 98337

## Slide 2
Status summary
Area | Status | Comment
Schedule | G | Sea-trial window holding for late March
Cost | A | Battery module invoice over plan (INV-20547)
Technical | G | Endurance bench test hit 58 days
Supply | A | Hydrophone lead time slipped 2 weeks
Document Reference: SLS-INT-0033
SLS-INTERNAL // INTERNAL USE ONLY
salish.systems

## Slide 3
Key milestones
Milestone | Target | Status
Endurance bench test complete | 2026-02-14 | On track
Integrated sea trial #1 | 2026-03-27 | On track
Customer demonstration | 2026-05-09 | Planning
Document Reference: SLS-INT-0033
SLS-INTERNAL // INTERNAL USE ONLY
salish.systems

## Slide 4
Test results to date
58 d
bench endurance
6,500 nm
range @ 6 kt
SS5
transit sea-state
Level 4
autonomy (CEDAR)
Document Reference: SLS-INT-0033
SLS-INTERNAL // INTERNAL USE ONLY
salish.systems

## Slide 5
Risks & next steps
• Hydrophone supply slip — qualifying an alternate vendor (Northwater ETA +2 wk).
• Battery cost variance under review with Finance; not a breach.
• Finalize trial #1 test plan and range booking.
• Hold customer demo for 9 May (soft) pending trial #1 results.
Document Reference: SLS-INT-0033
SLS-INTERNAL // INTERNAL USE ONLY
salish.systems

## Slide 6
HERON / SLS-101
Internal Use Only